## Slide 1: Time Planning and Control Activity on Arrow (Arrow Diagramming Method)

## Slide 2
Visualize and define the activities.
Sequence the activities (Job Logic).
Estimate the activity duration.
Schedule the project or phase.
Allocate and balance resources.
Compare target, planned and actual dates and update as necessary.
Control the time schedule with respect to changes.
Processes of Time Planning and Control

## Slide 3
Each time-consuming activity (task) is portrayed by an arrow.
The tail and head of the arrow denote the start and finish of the activity whilst its duration is shown in brackets below.
The length of the arrow has no significance neither has its orientation.
ARROW DIAGRAM
Activity
] Duration]
Order and deliver the new machine
] 30]

## Slide 4
As means of further defining the point in time when an activity starts or finishes, start and finish events are added.
An event (= node = connector), unlike an activity, does not consume time or resources, it merely represents a point in time at which something or some things happen.
Numbers are given to the events to provide a unique identity to each activity.
The first event in a project schedule is the start of the project. The last event in a project schedule is the end of the project.
ARROW DIAGRAM

## Slide 5
20
10
Activity
[Duration]
Start Event
Finish Event
Activity identification numbers
called event numbers
Activity Identification

## Slide 7
i-j Numbers of Events
The node at the tail of an arrow is the i-node.
The node at the head of an arrow is the j-node
i
j
Activity
Duration

## Slide 8
The network (the graphical representation of a project plan) must have definite points of beginning and finish.
(The accuracy and usefulness of a network is dependent mainly upon intimate knowledge of the project itself, and upon the general qualities of judgment and skill of the planning personnel.)
The arrows originate at the right side of a node and terminate at the left side of a node.
Any two events may be directly connected by no more than one activity.
Use symbols to indicate crossovers to avoid misunderstanding.
Rules of Making Arrow Diagram

## Slide 9
20
10
30
A
B
Logical Relationships
Node “20” is the j-node for activity “A” and it is also the i-node for activity “B” then activity “A” is a predecessor to activity “B”.
In other words activity “B” is a successor to activity “A”.
Activity B depends on activity A.

## Slide 10
Logical Relationships
20
10
40
30
50
Succeeding activities
Event numbers must not be duplicated in a network.
j-node number greater than i-node number.

## Slide 11
Concurrent activities
80
120
160
170
180
190
Logical Relationships

## Slide 12
The network must be a logical representation of all the activities. Where necessary, "dummy activities" are used for:
  Unique numbering and
  Logical sequencing.
  Dummy activity is an arrow that represents merely a dependency of one activity upon another. A dummy activity carries a zero time. It is also called dependency arrow.
Rules of Making Arrow Diagram

## Slide 13
The following network shows incorrect activity numbering.
90
100
110
50
70
60
80
A
B
Dummy Activities

## Slide 14
For unique numbering, use dummies.
90
100
110
50
70
60
80
A
B
75
Dummy Activities

## Slide 15
70
50
30
10
90
110
80
60
40
20
100
120
Dummy Activities
For representing logical relationships, you may need dummies.

## Slide 16
There must be no "looping" in the network. The loop is an indication of faulty logic. The definition of one or more of the dependency relationships is not valid.
Rules of Making Arrow Diagram
130
120
100
90
110

## Slide 17
The network must be continuous (without unconnected activities).
Rules of Making Arrow Diagram
80
100
60
30
90
50
20
10
120
110
70
40

## Slide 18
Networks should have only one initial event and only one terminal event.
Rules of Making Arrow Diagram
60
30
90
50
20
10
120
110
70
40

## Slide 19
Before an activity may begin, all activities preceding it must be completed (the logical relationship between activities is finish to start).
Rules of Making Arrow Diagram

## Slide 20
Standard layout for recording data
Network Analysis (Computation)
Occurrence times of Events = Early and late timings of event occurrence = Early and late event times
Earliest
Event
Time
Latest
Event
Time
Event
Label
Activity
Tail
Head
Activity

## Slide 21
Early Event Time (EET = E =TE)
Forward Pass for Computing EET
Each activity starts as soon as possible, i.e., as soon as all of its predecessor activities are completed.
Direction: Left to right, from the beginning to the end of the project
Set: EET of the initial node = 0
Add: EETj = EETi + Dij
Take the maximum
The estimated project duration = EET of the last node.
Early Event Time (Earliest occurrence time for event) is the earliest time at which an event can occur, considering the duration of precedent activities.
j
i
EETj
EETi
Activity
Dij

## Slide 22
0
1
10
20
3
3
A
B
8
30
4
C
40
12
Early Event Times (EET = E =TE)

## Slide 23
Early Event Times (TE)
12
40
80
4
5
9
K
L
M
50
15
70
24
4

## Slide 24
Early Event Times (TE)
20
10
30
50
40
60
70
2
3
3
4
3
1
5
4
7

## Slide 25
Early Event Times (TE)
20
10
0
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
2
4

## Slide 26
Late Event Time (LET = L =TL)
Backward Pass for Computing LET
Direction: Right to left, from the end to the beginning of the project
Set: LET of the last (terminal) node = EET for it
Subtract: LETi = LETj - Dij
Take the minimum
Late Event Time (Latest occurrence time of event) is the latest time at which an event can occur, if the project is to be completed on schedule.
j
i
LETi
EETj
LETj
EETi
Activity
Dij

## Slide 27
Late Event Times (TL)
8
13
50
16
16
9
9
3
7
40
60

## Slide 28
Late Event Times (TL)
2
20
10
0
4
30
50
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
40

## Slide 29
Late Event Times (TL)
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 30
Network Analysis (Computation)
Early Start (ES): The earliest time at which an activity can be started.
ESij = EETi
Early Finish (EF): The earliest time at which an activity can be completed.
EFij = ESij + Dij
Late Finish (LF): The latest time at which an activity can be completed without delaying project completion.
LFij = LETj
Late Start (LS): The latest time at which an activity can be started.
LSij = LFij  Dij
Activity Times (Schedule)

## Slide 31
Example: Activity Times
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0
ES20-50 = EET20 = 2
EF20-50 = ES + D = 2 + 3 = 5
LF20-50 = LET50 = 13
LS20-50 = LF – D = 13 – 3 = 10

## Slide 32
Network Analysis (Computation)
Total Float (TF)
Total float or path float is the amount of time that an activity’s completion may be delayed without extending project completion time.
Total float or path float is the amount of time that an activity’s completion may be delayed without affecting the earliest start of any activity on the network critical path.
Activity Floats

## Slide 33
Network Analysis (Computation)
Total Float (TF)
Total path float time for activity (i-j) is the total float associated with a path.
For arbitrary activity (ij), the total float can be written as:
Path Float =Total Float (TFij)
= LSij  ESij
= LFij  EFij
= LETj – EETi  Dij
Activity Floats

## Slide 34
Example: Total Float Times
TF20-50 = LS20-50 - ES20-50
TF20-50 = 10 – 2 = 8
TF20-50 = LF20-50 - EF20-50
TF20-50 = 13 – 5 = 8
TF20-50 = LET50 – EET20 - D20-50
TF20-50 = 13 – 2 - 3 = 8
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 35
Network Analysis (Computation)
Free Float (FF)
  Free float or activity float is the amount of time that an activity’s completion time may be delayed without affecting the earliest start of succeeding activity.
  Activity float is “owned” by an individual activity, whereas path or total float is shared by all activities along a slack path.
  Total float equals or exceeds free float (TF ≥ FF).
  For arbitrary activity (ij), the free float can be written as:
Activity Float = Free Float (FFij)
= ESjk  EFij
= EETj – EETi  Dij
Activity Floats

## Slide 36
FF20-50 = ES50-70 - EF20-50
FF20-50 = 8 – 5 = 3
FF20-50 = EET50 – EET20 - D20-50
FF20-50 = 8 – 2 - 3 = 3
Example: Free Float Times
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 37
Network Analysis (Computation)
Interfering Float (ITF)
  Interfering float is the difference between TF and FF.
  If ITF of an activity is used, the start of some succeeding activities will be delayed beyond its ES.
  In other words, if the activity uses its ITF, it “interferes” by this amount with the early times for the down path activity.
  For arbitrary activity (ij), the Interfering float can be written as:
Interfering Float (ITFij)
= TFij  FFij
= LETj  EETj
Activity Floats

## Slide 38
ITF20-50 = TF20-50 - FF20-50
IFF20-50 = 8 – 3 = 5
ITF20-50 = LET50 – EET50
ITF20-50 = 13 – 8 = 5
Example: Interfering Float Times
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 39
Network Analysis (Computation)
Independent Float (IDF)
  It is the amount of float which an activity will always possess no matter how early or late it or its predecessors and successors are.
  The activity has this float “independent” of any slippage of predecessors and any allowable start time of successors. Assuming all predecessors end as late as possible and successors start as early as possible.
  IDF is “owned” by one activity.
  In all cases, independent float is always less than or equal to free float (IDF ≤ FF).
Activity Floats

## Slide 40
Network Analysis (Computation)
Independent Float (IDF)
  For arbitrary activity (ij), the Independent Float can be written as:
Independent Float (IDFij)
= Max (0, EETj  LETi – Dij)
= Max (0, Min (ESjk) - Max (LFhi)  Dij)
Activity Floats

## Slide 41
Example: Independent Float Times
IDF20-50 = Max. (0, [EET50 – LET20 - D20-50])
IDF20-50 = Max. (0, [8 – 10 – 3]) = 0
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 42
Network Analysis (Computation)
  Critical path is the path with the least total float = The longest path through the network.
Critical Path
Subcritical Paths
  Subcritical paths have varying degree of path float and hence depart from criticality by varying amounts.
  Subcritical paths can be found in the following way:
    Sort the activities in the network by their path float, placing those activities with a common path float in the same group.
    Order the activities within a group by early start time.
    Order the groups according to the magnitude of their path float, small values first.

## Slide 43
Draw an arrow diagram to represent the following project. Calculate occurrence times of events, activity times, and activity floats. Also determine the critical path and the degree of criticality of other float paths.
Activity | Preceding Activity | Time (days)
A | None | 5
B | A | 7
C | A | 4
D | A | 8
E | B | 6
F | D | 8
G | E, C, F | 3
H | G | 4
I | G | 6
Example

## Slide 44
Example
80
20
50
60
70
30
40
[7]
[5]
[8]
[4]
[3]
[4]
[8]
[6]
A
B
C
D
E
F
G
H
0
0
10
5
5
12
15
28
24
24
21
21
13
13
30
30
30
6
I
Activity on arrow network and occurrence times of events

## Slide 45
Activity | ES | EF | LF | LS | TF | FF | ITF | IDF
A | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
B | 5 | 12 | 15 | 8 | 3 | 0 | 3 | 0
C | 5 | 9 | 21 | 17 | 12 | 12 | 0 | 12
D | 5 | 13 | 13 | 5 | 0 | 0 | 0 | 0
E | 12 | 18 | 21 | 15 | 3 | 3 | 0 | 0
F | 13 | 21 | 21 | 13 | 0 | 0 | 0 | 0
G | 21 | 24 | 24 | 21 | 0 | 0 | 0 | 0
H | 24 | 28 | 30 | 26 | 2 | 2 | 0 | 2
I | 24 | 30 | 30 | 24 | 0 | 0 | 0 | 0
Activity times and activity floats
Example

## Slide 46
Activity | ES | EF | LF | LS | TF | Criticality
A | 0 | 5 | 5 | 0 | 0 | Critical Path
D | 5 | 13 | 13 | 5 | 0 | 
F | 13 | 21 | 21 | 13 | 0 | 
G | 21 | 24 | 24 | 21 | 0 | 
I | 24 | 30 | 30 | 24 | 0 | 
H | 24 | 28 | 30 | 26 | 2 | a “near critical” path
B | 5 | 12 | 15 | 8 | 3 | Third most critical path
E | 12 | 18 | 21 | 15 | 3 | 
C | 5 | 9 | 21 | 17 | 12 | Path having most float
Critical path and subcritical paths
Example

## Slide 47
Installation of a new machine and training the operator
Activity Code | Activity Description | Depends on | Level | Duration (day)
100 | Inspect the machine after installation | 300 | 4 | 1
200 | Hire the operator | None | 1 | 25
300 | Install the new machine | 500, 400 | 3 | 2
400 | Inspect and store the machine after delivery | 700 | 2 | 1
500 | Hire labor to install the new machine | None | 1 | 20
600 | Train the operator | 200, 300 | 4 | 3
700 | Order and deliver the new machine | None | 1 | 30
Case Study

## Slide 48
Case Study: Installation of a New Machine and Training the Operator
30
30
1
1
30
0
2
20
3
25
36
33
33
31
10
0
60
50
40
30
20
31
33
33
36
Hire the operator
Hire labor to install the new machine
Order & deliver the machine
Inspect the machine after delivery
Install the m.
Inspect the m.
Train the operator

## Slide 49
Activity | i-j number | ES | EF | LS | LF | TF | FF | ITF | IDF
Hire the operator | 10-50 | 0 | 25 | 8 | 33 | 8 | 8 | 0 | 8
Hire labor to install the machine | 10-30 | 0 | 20 | 11 | 31 | 11 | 11 | 0 | 11
Order and deliver the machine | 10-20 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0
Inspect the m. after delivery | 20-30 | 30 | 31 | 30 | 31 | 0 | 0 | 0 | 0
Install the machine | 30-40 | 31 | 33 | 31 | 33 | 0 | 0 | 0 | 0
Inspect the machine | 40-60 | 33 | 34 | 35 | 36 | 2 | 2 | 0 | 2
Train the operator | 50-60 | 33 | 36 | 33 | 36 | 0 | 0 | 0 | 0
Activity times and activity floats
Case Study: Installation of a New Machine and Training the Operator
Critical path: 10-20, 20-30, 30-40, 50-60.
Near critical path: 40-60
Third most critical path: 10-50
Path having most float: 10-30

## Slide 50
CPM: Critical Path Method
Path
  Sequence of activities that leads from the starting node to the finishing node
Critical path
  The longest path; determines expected project duration
Critical activities
  Activities on the critical path
Slack
  Allowable slippage for path; the difference the length of path and the length of critical path

## Slide 51
Project Network – Activity on Arrow
1
2
3
4
5
6
Locate facilities
Order
setup
Interview
Hire and train
Remodel
Move in
AOA

## Slide 52
17-52
Project Network – Activity on Node
1
2
3
5
6
Locate facilities
Order furniture
Furniture setup
Interview
Remodel
Move in
4
Hire and train
7
S
AON

## Slide 53
A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
A comes before B, which comes before C
(a)
A
B
C
B
A
C
A and B must both be completed before C can start
(b)
A
C
C
B
A
B
B and C cannot begin until A is completed
(c)
B
A
C
A
B
C

## Slide 54
A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
C and D cannot begin until A and B have both been completed
(d)
A
B
C
D
B
A
C
D
C cannot begin until both A and B are completed; D cannot begin until B is completed. A dummy activity is introduced in AOA
(e)
C
A
B
D
A
B
C
D

## Slide 55
A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
B and C cannot begin until A is completed. D cannot begin until both B and C are completed. A dummy activity is again introduced in AOA.
(f)
A
C
D
B
A
B
C
D
Dummy activity

## Slide 56: Computing Algorithm
Network activities
  ES: earliest start
  EF: earliest finish
  LS: latest start
  LF: latest finish
Used to determine
  Expected project duration
  Slack time
  Critical path

## Slide 57: Determining the Project Schedule
Perform a Critical Path Analysis
Table 3.2
Activity Description Time (weeks)
A Build internal components 2
B Modify roof and floor 3
C Construct collection stack 2
D Pour concrete and install frame 4
E Build high-temperature burner 4
F Install pollution control system 3
G Install air pollution device 5
H Inspect and test 2
Total Time (weeks) 25
Earliest start (ES) = earliest time at which an activity can start, assuming all predecessors have been completed
Earliest finish (EF) = earliest time at which an activity can be finished
Latest start (LS) = latest time at which an activity can start so as to not delay the completion time of the entire project
Latest finish (LF) = latest time by which an activity has to be finished so as to not delay the completion time of the entire project

## Slide 58: AON Example
Activity | Description | Immediate Predecessors
A | Build internal components | —
B | Modify roof and floor | —
C | Construct collection stack | A
D | Pour concrete and install frame | A, B
E | Build high-temperature burner | C
F | Install pollution control system | C
G | Install air pollution device | D, E
H | Inspect and test | F, G
Milwaukee Paper Manufacturing's Activities and Predecessors

## Slide 59: AON Network for Milwaukee Paper
A
Start
B
Start Activity
Activity A
(Build Internal Components)
Activity B
(Modify Roof and Floor)

## Slide 60: AON Network for Milwaukee Paper
C
D
A
Start
B
Activity A Precedes Activity C
Activities A and B Precede Activity D

## Slide 61: AON Network for Milwaukee Paper
G
E
F
H
C
A
Start
D
B
Arrows Show Precedence Relationships

## Slide 62: AOA Network for Milwaukee Paper
H
(Inspect/ Test)
7
Dummy Activity
6
F
(Install Controls)
E
(Build Burner)
G
(Install Pollution Device)
5
D
(Pour Concrete/ Install Frame)
4
C
(Construct Stack)
1
3
2
B
(Modify Roof/Floor)
A
(Build Internal Components)

## Slide 63: Determining the Project Schedule
Perform a Critical Path Analysis
Activity Description Time (weeks)
A Build internal components 2
B Modify roof and floor 3
C Construct collection stack 2
D Pour concrete and install frame 4
E Build high-temperature burner 4
F Install pollution control system 3
G Install air pollution device 5
H Inspect and test 2
Total Time (weeks) 25

## Slide 64: Determining the Project Schedule
Perform a Critical Path Analysis
A
Activity Name or Symbol
Earliest Start
ES
Earliest Finish
EF
Latest Start
LS
Latest Finish
LF
Activity Duration
2

## Slide 65: ES/EF Network for Milwaukee Paper (Forward pass)
Start
0
0
ES
0
EF = ES + Activity time

## Slide 66: ES/EF Network for Milwaukee Paper
Start
0
0
0
A
2
2
EF of A = ES of A + 2
0
ES of A

## Slide 67: ES/EF Network for Milwaukee Paper
B
3
Start
0
0
0
A
2
2
0
3
EF of B = ES of B + 3
0
ES of B

## Slide 68: ES/EF Network for Milwaukee Paper
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0

## Slide 69: ES/EF Network for Milwaukee Paper
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
D
4
7
3
= Max (2, 3)

## Slide 70: ES/EF Network for Milwaukee Paper
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0

## Slide 71: ES/EF Network for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0

## Slide 72: LS/LF Times for Milwaukee Paper (Backward pass)
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = EF of Project
15
13
LS = LF – Activity time

## Slide 73: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = Min(LS of following activity)
10
13

## Slide 74: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = Min(4, 10)
4
2

## Slide 75: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
4
2
8
4
2
0
4
1
0
0

## Slide 76: Computing Slack Time
After computing the ES, EF, LS, and LF times for all activities, compute the slack or free time for each activity
Slack is the length of time an activity can be delayed without delaying the entire project
Slack = LS – ES or Slack = LF – EF

## Slide 77: Computing Slack Time
Earliest Earliest Latest Latest On Start Finish Start Finish Slack Critical Activity ES EF LS LF LS – ES Path
A 0 2 0 2 0 Yes
B 0 3 1 4 1 No
C 2 4 2 4 0 Yes
D 3 7 4 8 1 No
E 4 8 4 8 0 Yes
F 4 7 10 13 6 No
G 8 13 8 13 0 Yes
H 13 15 13 15 0 Yes

## Slide 78: Critical Path for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
4
2
8
4
2
0
4
1
0
0

## Slide 79: ES – EF Gantt Chart for Milwaukee Paper
A Build internal components
B Modify roof and floor
C Construct collection stack
D Pour concrete and install frame
E Build high-temperature burner
F Install pollution control system
G Install air pollution device
H Inspect and test
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16

## Slide 80: LS – LF Gantt Chart for Milwaukee Paper
A Build internal components
B Modify roof and floor
C Construct collection stack
D Pour concrete and install frame
E Build high-temperature burner
F Install pollution control system
G Install air pollution device
H Inspect and test
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16

## Slide 81: Critical Path Example
Perform a Critical Path Analysis
Activity Immediate Predecessors Time (weeks)
A - 6
B - 7
C A 3
D A 2
E B 4
F B 6
G C, E 10
H D, F 7

## Slide 82
H
7
13
20
14
21
F
6
7
13
8
14
G
10
11
21
11
21
E
4
7
11
7
11
C
3
6
9
11
8
D
2
6
8
14
12
A
6
6
0
8
2
B
7
0
7
0
7
Start
0
0
0
0
0
End
21
0
21
21
21

## Slide 83: Computing Slack Time
Earliest Earliest Latest Latest On Start Finish Start Finish Slack Critical Activity ES EF LS LF LS – ES Path
A 0 6 2 8 2 No
B 0 7 0 7 0 Yes
C 6 9 8 11 2 No
D 6 8 12 14 6 No
E 7 11 7 11 0 Yes
F 7 13 8 14 1 No
G 11 21 11 21 0 Yes
H 13 20 14 21 1 No

## Slide 84: Time Estimates
Deterministic
  Time estimates that are fairly certain
Probabilistic
  Estimates of times that allow for variation

## Slide 85
PERT: Program Evaluation and Review Technique

## Slide 86: Probabilistic Time Estimates
Optimistic time
  Time required under optimal conditions
Pessimistic time
  Time required under worst conditions
Most likely time
  Most probable length of time that will be required

## Slide 87
3-Points is a technique that involves people that are professional in the task we are estimating by this technique. In three-point estimation, three figures are produced initially for every distribution that is required, based on prior experience or best-guesses:
The first is a most likely (M)/best guess (BG) which is the average amount of work the task might take if the team member performed it 100 times.
The second estimate is the pessimistic (P) estimate which is the amount of work the task might take if the negative factors they identified do occur.
The third estimate is the optimistic (O) estimate which is the amount of work the task might take if the positive risks they identified do occur.

## Slide 88
Application
Two popular formula:
1. Triangular distribution:
Triangular Distribution: E = (o + m + p ) / 3
where E is Estimate; o = optimistic estimate;
p = pessimistic estimate; m = most likely estimate
2. Beta (or PERT):
Beta Distribution (PERT): E = (o + 4m + p ) / 6
The beta distribution is a weighted average in which more weight is given to the most likely estimate. This alteration to the formula and placing more weight on the most likely estimate is made to increase the accuracy of the estimate by making it follow the Normal Distribution shape. Hence, in most of the cases, the Beta (PERT) distribution has been proven to be more accurate than the 3-Point triangular estimation.
By using beta distribution you can determine the level of certainty of this prediction The variance is obtained by the difference between the pessimistic and the optimistic forecast divided by six squared

## Slide 89
Other Estimating Techniques
Bottom-Up estimate
Parametric estimates
Analogous estimates

## Slide 90: Probabilistic Estimates
Activity
start
Optimistic time
Most likely
time (mode)
Pessimistic
time
to
tp
tm
te
Beta Distribution

## Slide 91: Expected Time
te
=
to + 4tm +tp 6
te = expected time
to = optimistic time
tm = most likely time
tp = pessimistic time

## Slide 92: Variance
2 =
(tp – to)2
36
2 = variance
to = optimistic time
tp = pessimistic time

## Slide 93: Computing Variance
Most Expected Optimistic Likely Pessimistic Time Variance Activity a m b t = (a + 4m + b)/6 [(b – a)/6]2
A 1 2 3 2 .11
B 2 3 4 3 .11
C 1 2 3 2 .11
D 2 4 6 4 .44
E 1 4 7 4 1.00
F 1 2 9 3 1.78
G 3 4 11 5 1.78
H 1 2 3 2 .11

## Slide 94: Probability of Project Completion
Project variance is computed by summing the variances of critical activities
s2 = Project variance
= (variances of activities on critical path)
p

## Slide 95: Probability of Project Completion
Project variance is computed by summing the variances of critical activities
Project variance
s2 = .11 + .11 + 1.00 + 1.78 + .11 = 3.11
Project standard deviation
sp = Project variance
= 3.11 = 1.76 weeks
p

## Slide 96: Probability of Project Completion
PERT makes two more assumptions:
Total project completion times follow a normal probability distribution
Activity times are statistically independent
*Project Evaluation and Review Technique [PERT]

## Slide 97: Probability of Project Completion
Standard deviation = 1.76 weeks
15 Weeks
(Expected Completion Time)
Project standard deviation
Project variance
=s2 P
=sP

## Slide 98: Probability of Project Completion
What is the probability this project can be completed on or before the 16 week deadline?
Z = – /sp
= (16 wks – 15 wks)/1.76
= 0.57
due expected date date of completion
Where Z is the number of standard deviations the due date lies from the mean

## Slide 99: Probability of Project Completion
Z = − /sp
= (16 wks − 15 wks)/1.76
= 0.57
due expected date date of completion
Where Z is the number of standard deviations the due date lies from the mean
.00 .01 .07 .08
.1 .50000 .50399 .52790 .53188
.2 .53983 .54380 .56749 .57142
.5 .69146 .69497 .71566 .71904
.6 .72575 .72907 .74857 .75175

## Slide 100: Probability of Project Completion
Time
Probability (T ≤ 16 weeks) is 71.57%
0.57 Standard deviations
15 16 Weeks Weeks

## Slide 101: Determining Project Completion Time
Probability of 0.01
Z
Z = 2.33
Probability of 0.99
2.33 Standard deviations
0
2.33
Due date = 15 + 2.33 x 1.76
= 19.1 weeks
Z= due date– expected date of completion /sp

## Slide 102: PERT Example
Most Expected Optimistic Likely Pessimistic Time Variance Activity a m b t = (a + 4m + b)/6 [(b – a)/6]2
A 3 6 8 5.83 0.69
B 2 4 4 3.67 0.11
C 1 2 3 2.00 0.11
D 6 7 8 7.00 0.11
E 2 4 6 4.00 0.44
F 6 10 14 10.00 1.78
G 1 2 4 2.17 0.25
H 3 6 9 6.00 1.00
I 10 11 12 11.00 0.11 J 14 16 20 16.33 1.00
K 2 8 10 7.33 1.78
Immediate
Predecessors
-
-
-
C
B,D
A,E
A,E
F
G
C
H,I

## Slide 103: Time-cost Trade-offs: Crashing
Crash – shortening activity duration
Procedure for crashing
  Crash the project one period at a time
  Only an activity on the critical path
  Crash the least expensive activity
  Multiple critical paths: find the sum of crashing the least expensive activity on each critical path

## Slide 104: Crashing The Project
Time (Wks) Cost ($) Crash Cost Critical Activity Normal Crash Normal Crash Per Wk ($) Path?
A 2 1 22,000 22,750 750 Yes
B 3 1 30,000 34,000 2,000 No
C 2 1 26,000 27,000 1,000 Yes
D 4 2 48,000 49,000 1,000 No
E 4 2 56,000 58,000 1,000 Yes
F 3 2 30,000 30,500 500 No
G 5 2 80,000 84,500 1,500 Yes
H 2 1 16,000 19,000 3,000 Yes
308,000

## Slide 105: Crash and Normal Times and Costs for Activity B
| | |
1 2 3 Time (Weeks)
$34,000 —
$33,000 —
$32,000 —
$31,000 —
$30,000 —
—
Activity Cost
Crash
Normal
Crash Time
Normal Time
Crash Cost
Normal Cost
Crash Cost/Wk =
Crash Cost – Normal Cost
Normal Time – Crash Time
=
$34,000 – $30,000
3 – 1
= = $2,000/Wk
$4,000
2 Wks

## Slide 106: Advantages of PERT
Forces managers to organize
Provides graphic display of activities
Identifies
  Critical activities
  Slack activities
1
2
3
4
5
6

## Slide 107: Limitations of PERT
Important activities may be omitted
Precedence relationships may not be correct
Estimates may include a fudge factor
May focus solely on critical path
1
2
3
4
5
6
142 weeks

## Slide 108
Project Activity Variance

## Slide 109
Variances of Each Path through the Network

## Slide 110
Calculating the Probability of Completing the Project in Less Than a Specified Time
When you know:
  The expected completion time
  Its variance
You can calculate the probability of completing the project in “X” weeks with the following formula:
Where DT = the specified project completion time
EFP = the expected completion time of the path

## Slide 111
Example: Calculating the probability of finishing the project in 48 weeks
Use the z values in Appendix B to determine probabilities
E.G. for path 1