## Slide 1: 7.11 PERT/COST
PERT/Cost helps management gauge progress [measurement/test progress] against scheduled time and cost estimates.
PERT/Cost is based on analyzing a segmented project. Each segment is a collection of work packages.
PROJECT
Work Package 1
Activity 1
Activity 2
Work Package 2
Activity 3
Activity 5
Work Package 3
Activity 4
Activity 6

## Slide 2: Work Package - Assumptions
Once started, a work package is performed
continuously until it is finished.
The costs associated with a work package are spread
evenly throughout its duration.

## Slide 3: Monitoring Project progress
For each work package determine:
  Work Package Forecasted Weekly cost = Budgeted Total Cost for Work Package
Expected Completion Time for Work Package (weeks)
Value of Work to date = p(Budget for the work package) where p is the estimated percentage of the work package completed.
Expected remaining completion time = (1 – p)(Original Expected Completion Time)

## Slide 4: Monitoring Project progress
Completion Time Analysis
Use the expected remaining completion time estimates,
to revise the project completion time.
Cost Overrun/Underrun Analysis For each work package (completed or in progress) calculate Cost overrun = [Actual Expenditures to Date] - [Value of Work to Date]

## Slide 5: Monitoring Project Progress – Corrective Actions
A project may be found to be behind schedule, and or experiencing cost overruns.
Management seeks out causes such as:
  Mistaken project completion time and cost estimates.
  Mistaken work package completion times estimates and cost estimates.
  Problematic departments or contractors that cause delays.

## Slide 6: Monitoring Project Progress – Corrective Actions
Possible Corrective actions, to be taken whenever needed.
  Focus on uncompleted activities.
  Determine whether crashing activities is desirable.
  In the case of cost underrun, channel more resources to problem activities.
  Reduce resource allocation to non-critical activities.

## Slide 7: TOM LARKIN’s MAYORAL CAMPAIGN
Tom Larkin is running for Mayor.
Twenty weeks before the election the campaign remaining activities need to be assessed.
If the campaign is not on target or not within budget, recommendations for corrective actions are required.

## Slide 8: MAYORAL CAMPAIGN – Status Report
Work packages to focus on

## Slide 9: MAYORAL CAMPAIGN – Project Cost Control
Estimated work value to date=(13,000)(0.40)=$5,200
Cost overrun = 5600 - 5200 = 400

## Slide 10: MAYORAL CAMPAIGN – Completion Time Analysis
  The remaining network at the end of week 20.
I
9
Finish
F
7.8
H
15
(1-p)(original expected completion time)=(1-0.25)(20)=15
20+15=35
20+7.8=27.8
27.8+9=36.8
.8
The remaining activities are expected to take
0.8 weeks longer than the deadline of 36 weeks.

## Slide 11: MAYORAL CAMPAIGN – Results Summary
The project is currently .8 weeks behind schedule
There is a cost over-run of $3900.
The remaining completion time for uncompleted work packages is:
  Work package F: 7.8 weeks,
  Work package H: 15 weeks,
  Work package I: 9 weeks.
Cost over-run is observed in
  Work package F: $400,
  Work package H: $500.